## Sheet1
				Submitted, Investigating, Fixed, Wont Fix	Notes
Bugs for Chess Game	Date	Severity	Steps to Reproduce	Resolution
Placed piece changes color	12/06/18	Med	Middle click a piece in Setup mode, choose a color from the color menu	Fixed	Piece menu needed to make its piece reference unique and only pass copies
Can select opposing pieces	12/06/18	Med	Start a game in Single Player, you can select black pieces	Fixed	Check playerToMove before allowing selection
Cannot cancel starting a game	12/06/18	High	Choose Single Player from Mode menu, press cancel, game still begins, you can select and move pieces, etc.	Fixed	Mode was set in menu actionPerformed, before GameFrame handler
Move list is unbalanced	12/12/18	Low	Start SP game, play > 20 moves, black move on top will be off	Submitted

				Submitted, Investigating, Done, Won’t Do
Enhancements	Date	Priority	Description	Resolution
Highlight possible move choices	01/19/19	Low		Submitted
Cursor changes when over a piece	01/19/19	Low	When hovering over a square that has a piece, the cursor should change to a different shape to indicate an action is possible	Done
Allow Promotion	01/19/19	High		Submitted
Timer for players should switch	01/19/19	Med		Submitted
Play as black	01/19/19	Med		Submitted
+ for check, # for checkmate	01/19/19	Low		Submitted
Have computer consider castling	01/19/19	Low		Submitted
Parameterize AI difficulty	01/19/19	Med		Submitted
Sounds	01/19/19	Low		Submitted
Multiplayer over internet	01/19/19	Med		Submitted
Consolidate GameRequest logic	01/19/19	Low	GameRequests are created in GameFrame and processed in GameController. This means that two separate files have to be in perfect sync	Submitted