## Sheet1
Bugs for Chess Game				Submitted, Investigating, Fixed, Wont Fix	Notes
Title	Date	Severity	Steps to Reproduce	Resolution
Placed piece changes color	12/06/18	Med	Middle click a piece in Setup mode, choose a color from the color menu	Fixed	Piece menu needed to make its piece reference unique and only pass copies
Can select opposing pieces	12/06/18	Med	Start a game in Single Player, you can select black pieces	Fixed	Check playerToMove before allowing selection
Cannot cancel starting a game	12/06/18	High	Choose Single Player from Mode menu, press cancel, game still begins, you can select and move pieces, etc.	Fixed	Mode was set in menu actionPerformed, before GameFrame handler
Move list is unbalanced	12/12/18	Low	Start SP game, play > 20 moves, black move on top will be off	Submitted

Enhancements
Highlight possible move choices
Cursor changes when over a piece
Allow Promotion
Timer for players should switch
Play as black
+ for check, # for checkmate
Have computer consider castling
Parameterize AI difficulty
Sounds
Multiplayer over internet